## Sheet1
Task ID | Task Name | Phase | Sprint | Owner | Status | Start Date | End Date | Planned Days | Actual Days
T1 | Requirement Gathering | Planning | Sprint 1 | PM | Done | 2026-04-01 | 2026-04-03 | 3 | 3
T2 | Stakeholder Alignment | Planning | Sprint 1 | PM | Done | 2026-04-04 | 2026-04-05 | 2 | 2
T3 | Wireframes | Design | Sprint 1 | Design | Done | 2026-04-06 | 2026-04-10 | 5 | 5
T4 | User Flow | Design | Sprint 1 | Design | Done | 2026-04-11 | 2026-04-13 | 3 | 4
T5 | Frontend Integration | Development | Sprint 2 | Eng | In Progress | 2026-04-14 | 2026-04-20 | 7 | 5
T6 | Backend Integration | Development | Sprint 2 | Eng | In Progress | 2026-04-14 | 2026-04-20 | 7 | 6
T7 | QA Testing | Testing | Sprint 3 | QA | To Do | 2026-04-21 | 2026-04-24 | 4 | 0
T8 | Bug Fixing | Testing | Sprint 3 | Eng | To Do | 2026-04-25 | 2026-04-27 | 3 | 0
T9 | Beta Release | Launch | Sprint 3 | PM | To Do | 2026-04-28 | 2026-04-29 | 2 | 0
T10 | Full Rollout | Launch | Sprint 3 | PM | To Do | 2026-04-30 | 2026-05-01 | 2 | 0